## Gantt Chart
Bright Coffee Shop Sales Analysis — Project Gantt Chart
Period: 24 Mar 2026 – 31 Mar 2026 ¦ Author: Siphamandla Moyo ¦ Due: 31 March 2026
Phase | Task | Owner | Start | End | 24 Mar | 25 Mar | 26 Mar | 27 Mar | 28 Mar | 29 Mar | 30 Mar | 31 Mar
PLANNING
Planning | Define project scope & objectives | Siphamandla | 24 Mar | 24 Mar
Planning | Design data architecture (Miro) | Siphamandla | 24 Mar | 25 Mar
Planning | Set up GitHub repository | Siphamandla | 25 Mar | 25 Mar
DATA PROCESSING
Data Processing | Convert Excel dataset to CSV | Siphamandla | 26 Mar | 26 Mar
Data Processing | Load CSV into Snowflake / DB | Siphamandla | 26 Mar | 26 Mar
Data Processing | Clean & transform data (SQL) | Siphamandla | 26 Mar | 27 Mar
Data Processing | Create time buckets & calculated fields | Siphamandla | 27 Mar | 27 Mar
ANALYSIS
Analysis | Revenue analysis by product category | Siphamandla | 27 Mar | 28 Mar
Analysis | Store performance analysis | Siphamandla | 28 Mar | 28 Mar
Analysis | Peak trading hours analysis | Siphamandla | 28 Mar | 28 Mar
Analysis | Monthly revenue trend analysis | Siphamandla | 28 Mar | 29 Mar
VISUALISATION
Visualisation | Build pivot tables in Excel | Siphamandla | 28 Mar | 29 Mar
Visualisation | Create charts & dashboards | Siphamandla | 29 Mar | 30 Mar
PRESENTATION
Presentation | Build PowerPoint slides (14 slides) | Siphamandla | 29 Mar | 30 Mar
Presentation | Write key insights & recommendations | Siphamandla | 30 Mar | 30 Mar
Presentation | Final review & proofreading | Siphamandla | 2026-03-30 | 2026-03-30
SUBMISSION
Submission | Push all files to GitHub | Siphamandla | 31 Mar | 31 Mar
Submission | Final submission check | Siphamandla | 31 Mar | 31 Mar
LEGEND |  | Planning
Data Processing
Analysis
Visualisation
Presentation
Submission